APPENDIX 1

Task 1

Design and manufacturing of three generations of demonstrators for critical technology feasibility studies. Duration: 2009 – 2010 .

| Subtasks and main milestones | Responsibility/Deadline | Resources |
| --- | --- | --- |
| Demonstrator 0-b-prime (3 pcs + 1 mock-up) The design of the demonstrator is similar to that of the Demonstrator 0-b (2008) with two major modifications: 1) usage of the CBM02B2 baby sensor instead of the previously used CBM01B2 and 2) realization of a possibility of reusing the boards with ERNI connectors after remounting the sensors. Goal: the demonstrators will be used as beam tracking sensors during the in-beam tests of other demonstrators (Task 2) and as samples for radiation tests (Task 5). | SE SRTIIE Sept 2009 | Parts needed: tested baby sensors (4 sensors tested by SINP are to be shipped from JINR to SE SRTIIE + 1-2 technological sensors), ERNI and LEMO connectors (GSI, August 2009), Budget = 15 kEu direct contract GSI-SE SRTIIE |
| Demonstrator 1-a (6 pcs – 2 pcs each length) A set of three microcable adapters of different length based on the prototypes of realistic microcables to be used as analogue cables in CBM STS. Goal: to bench test the performance of the read-out chain with long analogue cables. | SE SRTIIE Sept 2009 | ERNI connectors (GSI, August 2009), Budget = 15 kEu direct contract GSI-SE SRTIIE |
| Demonstrator 1-a-double (6 pcs – 2 pcs each length) A set of three microcable adapters of different types of grounding network but fixed length to be decided later based on the prototypes of realistic microcables to be used as analogue cables in CBM STS. The cables are made of two laminated microcables of a 100 um pitch with an optimized ground network in between the layers as in the D0-L0 analogue cables, or use other means to decrease the noise and cross-talk between the adjacent strips. Goal: first prototype of realistic analog microcable | SE SRTIIE Dec 2009 | ERNI connectors (GSI/ JINR, Oct 2009)/ Request for additional funding in 2009: R4AF = 3 kEu |
| Demonstrator 1-b (3 pcs) A combination of the Demonstrator 0-b-prime and Demonstrator 1-a with direct connection of the chosen type of the analogue cable to the board with a sensor (Task 2, Subtask 1). | SE SRTIIE Nov 2009 | tested baby sensors (3 sensors + 1-2 technological sensors), ERNI and LEMO connectors (GSI, August 2009), Budget = 15 kEu direct contract GSI-SE SRTIIE |
| Demonstrator 1-c (3 pcs + 1 mock-up) The similar type of the Demonstrator 1-b with major modification: using full-size sensor CBM01 (or CBM03/ISTC) instead of baby sensor. | SE SRTIIE Nov 2009 | tested sensors (3 sensors + 2 technological sensors), ERNI and LEMO connectors (GSI, August 2009), Budget = 15 kEu direct contract GSI-SE SRTIIE |
| Demonstrator 2-a (3 pcs) An electro-mechanical mock-up of the CBM STS module (3 sensors with serial strip connection) contains the sensors assembly and an analogue microcables of the type chosen from the results of the Demonstrator 1-b testing but with 1024 read-out lines connected to the backend hybrid mock-up or to the ERNI connector suitable for FEB and CF mechanical support. Foreseen as a step for the development of the Demonstrator 2-b. Demonstrator 2-b (or essential parts of it) is also foreseen to be used as a test sample of the Cooling System (CS) Demonstrator 1 (Task 3 Subtask 5). | SE SRTIIE Igolkin Dec 2009 | Dummy sensors from RIMST, Sept 2009, mechanical parts and auxiliary technological equipment for assembling (S. Igolkin, Nov, 2009), sensors assembly and an analogue microcables (SE SRTIIE, Nov, 2009) funding from ISTC project# 3540 and BMBF@JINR at 10kEu (for SE SRTIIE) |
| Demonstrator 2-b (3 pcs) Complete CBM STS module prototype connected via analogue cable 10-20 cm in length to the prototype of the readout hybrid electronics. | Consortium June 2010 | Tested sensors from RIMST or GSI, mechanical parts from KRI CF workshop (ISTC Pr. #3540). Prototype of the backend hybrid front end board from GSI, sensors assembly and analog microcables from SE SRTIIE. Additional funding needed. |
| Demonstrator 3-a (3 pcs) Electro-mechanical mock-up of the CBM STS ladder. | Consortium May 2010 | Sensors from RIMST and GSI, backend front-end mock-up and modules-mock-up bonded via microcables at SE SRTIIE, mechanical parts and auxiliary technological equipment for assembly (S. Igolkin, Nov. 2009). Funding: ISTC Project#3540 +BMBF@JINR |
| Demonstrator 3-b (1-2 pcs) Complete CBM STS ladder prototype | Consortium Sept 2010 | Sensors and modules from RIMST and GSI, backend hybrid front-end prototype from GSI bonded via microcables at SE SRTIIE. Technological equipment for assembling the demonstrator from KRI+JINR. Funding: ISTC Funding: ISTC Project#3540 +BMBF@JINR; extra funds are needed for manufacturing of the auxiliary technological equipment such as the assembly stand etc. (Request 4 Additional Funding for SE SRTIIE (subtasks 7-9) in 2010 30kEu + 15 kEu for technological equipment for assembling) |
| Requested deliverables, timelines, person in charge |
| Heuser: ERNI connectors- August 2009, Prepreg – August 2009, Contract GSI-SE SRTIIE – August 2009, additional CBM02B2 tested – August 2009 Schmidt: Backend hybrid front-end prototype – End 2010. Igolkin: CF parts for module – August 2009, auxiliary equipment for module assembly – August 2009 Borshchov: Demonstrator 0-b-prime – Sep 2009, Demonstrator 1-a – Sep 2009, Demonstrator 1-b – Nov 2009, Demonstrator 1-c – Nov 2009, Demonstrator 1-a-double – Dec 2009, Demonstrator 2-a – Dec 2009, Demonstrator 2-b – June 2009, Demonstrator 3-a – June 2010, Demonstrator 3-b – September 2010. |

Task 2

Bench and in-beam tests of demonstrators; Duration: 2009 – 2010.

| Subtasks and main milestones | Responsibility/Deadline | Fund source |
| --- | --- | --- |
| In GSI, Darmstadt: Bench tests of Demonstrator 0-b with n-XYTER readout boards In-beam tests of Demonstrator 0-b + n-XYTER readout with 2.5 GeV proton beam Bench test of Demonstrator 1-a Bench test of Demonstrator 1-b In-beam test of Demonstrator 1-b with 2.5 GeV proton beam In JINR, Dubna (bench) and IHEP, Protvino(in-beam): Bench tests of Demonstrators 0-b-prime and 1-a Mechanical design of the in-beam test station for Protvino November 2009 tests DAQ preparations for Protvino November 2009 tests Goal: conducting test experiments with a mixed trigger/ non-trigger scheme in Protvino in November 2009. Slow Control for Protvino tests Mounting demonstrators at the beam line in-front of the SVD2 beam-tracking stations, organization of visit of German experts | GSI Aug 2009 GSI September 2009 GSI March 2010 GSI June 2010 GSI Fall 2010 JINR Oct 2009 JINR Oct 2009 JINR Assistance – SVD2 and GSI Nov 2009 Korolev for JINR Oct 2009 Vorobjev Oct 2009 | GSI GSI GSI GSI GSI ISTC Pr. #3540 ISTC Pr .#3540 JINR : manufacture mechanics ISTC Pr.#3540 BMBF@JINR Request to GSI : 1) to reprogram FEB-ROC for a possibility to work in trigger mode, 2) to realize possibility for writing serial code into ROC ISTC Project #3540 JINR-BMBF funds for organization of the test run (level to be decided later) |
| Requested deliverables, timelines, person in charge |
| Schmidt: 3 FEB + 1 ROC for Protvino 2009 test run – October 2009, backend hybrid front-end prototype End 2010. Nomokonov (in assistance with Schmidt and Leflat-Volkov): DAQ for the in-beam tests - October 2009 Murin: (in assistance with Vorobjev and Budilov): In-beam test mechanics? Organization of - October 2009 test run in November |

Task 3

CF Mechanics and Cooling - Development of technical approaches and bench tests of prototypes: 
2009-2010.

| Subtasks and main milestones | Responsibility/Deadline | Funding |
| --- | --- | --- |
| Production of mechanical parts for Demonstrator 2-a Design of technological equipment for assembling Demonstrator 2-a Production of 3D CF spaceforms with the ALICE ITS mold for Demonstrator 3-a (5 pcs) Design of technological equipment for Demonstrator 3-a assembling (minimum set!) Design and manufacturing of the Cooling System (CS) Demonstrator 1 “MATRASIK” cooling technology bench tests with the CS Demonstrator 1 | Igolkin@ KRI, Dec 2009 Vorobiev@ IHEP June 2010 Igolkin@KRI Dec 2009 Igolkin+JINR (?) Igolkin+JINR (?) Igolkin+JINR (?) | ISTC Pr. #3540 Mechanical parts from KRI, cables and know-how from SE RTIIE, Additional funding Request for 2010 at level to be decided later ISTC Pr. #3540 ISTC Pr.#3540 BMBF@JINR ISTC Pr. #3540 BMBF@JINR ISTC Pr. #3540 BMBF@JINR |
| Requested deliverables, timelines, person in charge |
| Heuser: Prepreg – August 2009, Murin: auxiliary laboratory equipment for Subtask 6 |

Task 4

Russian-made Sensor Development for the CBM: 2009-2010. (Subject of signed ISTC-RIMST Contract)

| Subtasks and main milestones | Responsibility/Deadline | Funding |
| --- | --- | --- |
| 1. Production of 10 electro-mechanical 42х62 mm2 CBM STS mock-ups 2. Production of 20 wafers with 42х62 mm2 CBM STS mock-ups 3. Full characterization of all sensors produced, cutting of sensors for further use | Merkin, Oct 2009 Merkin, Apr 2010 Merkin, June 2010 | ISTC Pr. #3540 ISTC Pr. #3540 ISTC Pr. #3540 |
| Requested deliverables, timelines, person in charge |
| None. |

Task 5

Radiation tests of the CBM STS radiation sensitive parts at KRI Cyclotron: 2009-2010.

| Subtasks and main milestones | Responsibility/Deadline | Funding |
| --- | --- | --- |
| Irradiation of silicon pad detectors and prototypes of double-sided silicon strip detectors with fluences between 3×1012 and 3×1014 1-MeV nequiv. /cm2 Measurement of leakage currents (current degradation coefficients) and inter-strip resistance (for 3 to 5 strip pairs) on p- and n sides of the irradiated samples. Irradiation of radiation tolerant single-sided or double-sided silicon test structures with neutron fluences up to ~1015 n/cm2 for comparison with common test structures. | Jakovlev, Karmanov Oct. 09 – June 2010 Jakovlev, Karmanov Oct. 09 – June 2010 Optional if available through GSI | ISTC Pr. #3540 |
| Requested deliverables, timelines, person in charge |
| Heuser: CBM02B2 detectors with different biasing schemes – Oct. 2009 Merkin: Test diodes + test detectors from ISTC wafers – June 2010 Heuser: Test diodes from CBM03 wafers – June 2010 |